## Questionnaire
PROJECT INFORMATION |  |  | Instructions: Complete the Project Information and Risk and Complexity Questions. The results will calculate automatically when all questions have responses. Document the results on the Project Risk and Complexity page in EPMO. Documentation Requirements are based upon project Complexity and are in addtion to the project workflow requirements captured directly on the forms in EPMO. Note, if the Project Reporting Requirements Questionnaire yielded a "Non-Major" project and the Total Project Cost is < $100,000, the project will automatically be classified as "Basic" regardless of the complexity score calculated.
Project Name
Project Phase
Prepared By
Prepared Date
RESULTS |  |  | REQUIRED DOCUMENTATION (based on Project Complexity results)
Ratings will appear once all questions are answered Scores are interim until all questions are answered |  |  | Complete all Questions to display Results
Criteria | Score | Rating
Project Complexity | 0 | -
Budget Risk | 0 | -
External Dependency Risk | 0 | -
Management Risk | 0 | -
Mission Critical Risk | 0 | -
Risk of Failure | 0 | -
Complexity Risk | 0 | -
Overall Project Risk | 0 | -
QUESTIONS
Question Number | Risk and Complexity Question |  | Answer Lists (Note--when you click in each answer cell, a drop down list arrow will appear) | Check for Blank | Complexity Score | Risk Score | Risk Section
0 | What is the current Project Reporting & Oversight Classification? |  |  | TRUE
1 | What is the total project cost? |  |  | TRUE | 0 | 0 | Budget Risk
2 | What is the estimated total cost for hardware? |  |  | TRUE | 0 | 0
3 | What is the estimated total cost for software? |  |  | TRUE | 0 | 0
4 | What is the estimated cost of application development or software configuration services? |  |  | TRUE | 0 | 0
5 | How much confidence is there in the expenditure and funding projections? |  |  | TRUE | 0 | 0 | Budget Risk
6 | What percentage of the Mason's budget does the project represent? |  |  | TRUE | 0 | 0 | Budget Risk
7 | Have sufficient project funds been budgeted and allocated? |  |  | TRUE | 0 | 0 | Budget Risk
8 | Is the project sponsor fully resourcing the project? |  |  | TRUE | 0 | 0 | Management Risk
9 | What is the size of the Project Team (Full Time Equivalents)? |  |  | TRUE | 0 | 0
10 | What is the experience and training level of Mason's project managers? |  |  | TRUE | 0 | 0 | Management Risk
11 | What is the level of management commitment? |  |  | TRUE | 0 | 0 | Management Risk
12 | To what degree are the project team members collocated (same building/campus/etc.)? |  |  | TRUE | 0 | 0
13 | What is the project's duration? |  |  | TRUE | 0 | 0
14 | Is funding available for maintenance of the project deliverable after project closure? |  |  | TRUE | 0 | 0 | Budget Risk
15 | How much variation in the timeframe can be tolerated? |  |  | TRUE | 0 | 0
16 | Does this project require resources from other organizations outside ITS? |  |  | TRUE | 0 | 0 | External Dependency Risk
17 | Is this project dependent on another projects deliverable? |  |  | TRUE | 0 | 0 | External Dependency Risk
18 | Has Mason and/or the vendor executed a project similar to this before? |  |  | TRUE | 0 | 0 | Risk of Failure
19 | Does the project address State and Federal mandates? |  |  | TRUE | 0 | 0 | Mission Critical Risk
20 | How politically sensitive is the project? |  |  | TRUE | 0 | 0 | Risk of Failure
21 | How will the failure of the project impact the customers? |  |  | TRUE | 0 | 0 | Risk of Failure
22 | What is the anticipated involvement of the End Users with System Design and Testing? |  |  | TRUE | 0 | 0
23 | What is the anticipated involvement of the End Users in the Definition of Project Requirements and Scope? |  |  | TRUE | 0 | 0
24 | How important is the project to successful execution of Mason's core business activities? |  |  | TRUE | 0 | 0 | Mission Critical Risk
25 | How significant will the project’s impact be on the business process? |  |  | TRUE | 0 | 0 | Complexity Risk
26 | How large of an organizational impact will the project have in the Commonwealth (beyond the impact to just George Mason University)? |  |  | TRUE | 0 | 0 | Mission Critical Risk
27 | Is the project using proven technology? |  |  | TRUE | 0 | 0 | Complexity Risk
28 | Is the proposed solution applied in a New, Proven, or Tried way? |  |  | TRUE | 0 | 0 | Complexity Risk
29 | What level of Data Conversion is required for the project (impact and complexity)? |  |  | TRUE | 0 | 0 | External Dependency Risk
30 | What is the calculated Overall Risk level for the project? (Auto-filled from data above) |  | To Be Calculated |  | 0 | 0
|  |  |  | 30 | <--Verify all questions answered

## Responses
Question # | Question Text (Note - these values are auto updated based on the Complexity Question sheet's corresponding question) | Answer Choices | Complexity Score | Risk Score | Risk Category
0 | What is the current Project Reporting & Oversight Classification? |  | 0 | 0
0 | What is the current Project Reporting & Oversight Classification? | Non-Major Project | 0 | 0
0 | What is the current Project Reporting & Oversight Classification? | Internal Major Project | 0 | 0
0 | What is the current Project Reporting & Oversight Classification? | State Major Project | 0 | 0
1 | What is the total project cost? |  | 0 | 0 | Budget
1 | What is the total project cost? | Less than $100,000 | 10 | 0 | Budget
1 | What is the total project cost? | Between $100,000 and $500,000 | 20 | 1 | Budget
1 | What is the total project cost? | Between $500,000 and $1,000,000 | 30 | 3 | Budget
1 | What is the total project cost? | Greater than $1 Million | 40 | 5 | Budget
2 | What is the estimated total cost for hardware? |  | 0 | 0
2 | What is the estimated total cost for hardware? | Less than $100,000 | 2 | 0
2 | What is the estimated total cost for hardware? | Between $100,000 and $500,000 | 4 | 0
2 | What is the estimated total cost for hardware? | Between $500,000 and $1,000,000 | 6 | 0
2 | What is the estimated total cost for hardware? | Greater than $1 Million | 8 | 0
3 | What is the estimated total cost for software? |  | 0 | 0
3 | What is the estimated total cost for software? | Less than $100,000 | 2 | 0
3 | What is the estimated total cost for software? | Between $100,000 and $500,000 | 4 | 0
3 | What is the estimated total cost for software? | Between $500,000 and $1,000,000 | 6 | 0
3 | What is the estimated total cost for software? | Greater than $1 Million | 8 | 0
4 | What is the estimated cost of application development or software configuration services? |  | 0 | 0
4 | What is the estimated cost of application development or software configuration services? | Less than $100,000 | 2 | 0
4 | What is the estimated cost of application development or software configuration services? | Between $100,000 and $500,000 | 4 | 0
4 | What is the estimated cost of application development or software configuration services? | Between $500,000 and $1,000,000 | 6 | 0
4 | What is the estimated cost of application development or software configuration services? | Greater than $1 Million | 8 | 0
5 | How much confidence is there in the expenditure and funding projections? |  | 0 | 0 | Budget
5 | How much confidence is there in the expenditure and funding projections? | Accuracy of budget estimate is greater than 95% and less than or equal to 100%. | 2 | 0 | Budget
5 | How much confidence is there in the expenditure and funding projections? | Accuracy of budget estimate is greater than 85% and less than or equal to 95%. | 4 | 1 | Budget
5 | How much confidence is there in the expenditure and funding projections? | Accuracy of budget estimate is greater than 50% and less than or equal to 85% | 8 | 3 | Budget
5 | How much confidence is there in the expenditure and funding projections? | Accuracy of budget estimate is less than or equal to 50%. | 16 | 5 | Budget
6 | What percentage of the Mason's budget does the project represent? |  | 0 | 0 | Budget
6 | What percentage of the Mason's budget does the project represent? | Project is less than 2% of Mason's budget | 2 | 0 | Budget
6 | What percentage of the Mason's budget does the project represent? | Project is greater than or equal to 2% but less than 5% of Mason's budget | 4 | 1 | Budget
6 | What percentage of the Mason's budget does the project represent? | Project is greater than or equal to 5% and less than 15% of Mason's budget | 6 | 3 | Budget
6 | What percentage of the Mason's budget does the project represent? | Project is 15% or more of Mason's budget | 8 | 5 | Budget
7 | Have sufficient project funds been budgeted and allocated? |  |  | 0 | Budget
7 | Have sufficient project funds been budgeted and allocated? | All funding is budgeted and allocated. |  | 0 | Budget
7 | Have sufficient project funds been budgeted and allocated? | Minimum essential funding is budgeted and allocated. |  | 1 | Budget
7 | Have sufficient project funds been budgeted and allocated? | Funding is available but not allocated. |  | 3 | Budget
7 | Have sufficient project funds been budgeted and allocated? | Funding is not budgeted or allocated. |  | 5 | Budget
8 | Is the project sponsor fully resourcing the project? |  | 0 | 0 | Management
8 | Is the project sponsor fully resourcing the project? | Sponsor owns all the resources needed (within the chain of command) | 2 | 0 | Management
8 | Is the project sponsor fully resourcing the project? | Sponsor owns most of the resources needed (within the chain of command) | 4 | 1 | Management
8 | Is the project sponsor fully resourcing the project? | Sponsor has control of most of the resources needed (matrixed reporting) | 6 | 3 | Management
8 | Is the project sponsor fully resourcing the project? | Sponsor has control of some of the resources needed (matrixed reporting) | 12 | 5 | Management
9 | What is the size of the Project Team (Full Time Equivalents)? |  | 0 | 0
9 | What is the size of the Project Team (Full Time Equivalents)? | No full time FTEs assigned | 2 | 0
9 | What is the size of the Project Team (Full Time Equivalents)? | 1 to 2 people | 3 | 0
9 | What is the size of the Project Team (Full Time Equivalents)? | 2 to 5 people | 6 | 0
9 | What is the size of the Project Team (Full Time Equivalents)? | 5 or more people | 12 | 0
10 | What is the experience and training level of Mason's project managers? |  | 0 | 0 | Management
10 | What is the experience and training level of Mason's project managers? | Mason's project managers are well trained and very experienced. | 2 | 0 | Management
10 | What is the experience and training level of Mason's project managers? | Mason's project managers have training and experience. | 4 | 1 | Management
10 | What is the experience and training level of Mason's project managers? | Mason's project managers have some training or experience. | 8 | 3 | Management
10 | What is the experience and training level of Mason's project managers? | Mason's has no project managers. | 16 | 5 | Management
11 | What is the level of management commitment? |  | 0 | 0 | Management
11 | What is the level of management commitment? | Management has made the project a priority. | 0 | 0 | Management
11 | What is the level of management commitment? | Management is committed to the project. | 0 | 1 | Management
11 | What is the level of management commitment? | Management has demonstrated interest. | 0 | 3 | Management
11 | What is the level of management commitment? | Management is not committed. | 0 | 5 | Management
12 | To what degree are the project team members collocated (same building/campus/etc.)? |  | 0 | 0
12 | To what degree are the project team members collocated (same building/campus/etc.)? | 90-100% of the team in the same location | 1 | 0
12 | To what degree are the project team members collocated (same building/campus/etc.)? | 50%-90 of team in same location | 2 | 0
12 | To what degree are the project team members collocated (same building/campus/etc.)? | 25% - 50% of team in same location | 4 | 0
12 | To what degree are the project team members collocated (same building/campus/etc.)? | 25% or less of team in same location | 6 | 0
13 | What is the project's duration? |  | 0 | 0
13 | What is the project's duration? | Duration is less than 6 months | 2 | 0
13 | What is the project's duration? | Duration is 6 to 12 months | 4 | 0
13 | What is the project's duration? | Duration is 12 to 24 months | 8 | 0
13 | What is the project's duration? | Duration is greater than 24 months | 16 | 0
14 | Is funding available for maintenance of the project deliverable after project closure? |  |  | 0 | Budget
14 | Is funding available for maintenance of the project deliverable after project closure? | Maintenance funding is available. |  | 0 | Budget
14 | Is funding available for maintenance of the project deliverable after project closure? | Maintenance funding is planned and available. |  | 1 | Budget
14 | Is funding available for maintenance of the project deliverable after project closure? | Maintenance funding is planned but constrained. |  | 3 | Budget
14 | Is funding available for maintenance of the project deliverable after project closure? | Maintenance funding has not been planned. |  | 5 | Budget
15 | How much variation in the timeframe can be tolerated? |  | 0 | 0
15 | How much variation in the timeframe can be tolerated? | Schedule is not fixed and therefore highly flexible | 3 | 0
15 | How much variation in the timeframe can be tolerated? | Schedule can tolerate major variations | 6 | 0
15 | How much variation in the timeframe can be tolerated? | Schedule can tolerate minor variations | 9 | 0
15 | How much variation in the timeframe can be tolerated? | Schedule is fixed and can not be changed | 12 | 0
16 | Does this project require resources from other organizations outside ITS? |  | 0 | 0 | External
16 | Does this project require resources from other organizations outside ITS? | Project requires no external resources. | 3 | 0 | External
16 | Does this project require resources from other organizations outside ITS? | Project requires few external resources. | 6 | 1 | External
16 | Does this project require resources from other organizations outside ITS? | Project requires some external resources. | 9 | 3 | External
16 | Does this project require resources from other organizations outside ITS? | External resources are critical to the project. | 12 | 5 | External
17 | Is this project dependent on another projects deliverable? |  |  | 0 | External
17 | Is this project dependent on another projects deliverable? | No other deliverables are required. |  | 0 | External
17 | Is this project dependent on another projects deliverable? | Other deliverables enhance the project. |  | 1 | External
17 | Is this project dependent on another projects deliverable? | The project will utilize other project deliverables. |  | 3 | External
17 | Is this project dependent on another projects deliverable? | A project deliverable from another project is required. |  | 5 | External
18 | Has Mason and/or the vendor executed a project similar to this before? |  | 0 | 0 | Failure
18 | Has Mason and/or the vendor executed a project similar to this before? | Mason and the vendor(s) have executed many similar projects successfully | 2 | 0 | Failure
18 | Has Mason and/or the vendor executed a project similar to this before? | Mason or the vendor have executed several similar projects | 4 | 1 | Failure
18 | Has Mason and/or the vendor executed a project similar to this before? | Mason or the vendor have executed a similar project | 8 | 3 | Failure
18 | Has Mason and/or the vendor executed a project similar to this before? | Neither Mason nor the vendor has executed a similar project | 12 | 5 | Failure
19 | Does the project address State and Federal mandates? |  | 0 | 0 | Mission Critical
19 | Does the project address State and Federal mandates? | The project has little or no direct impact on accomplishment of State and Federal mandates | 2 | 0 | Mission Critical
19 | Does the project address State and Federal mandates? | The project enhances accomplishment of State and Federal mandates | 4 | 1 | Mission Critical
19 | Does the project address State and Federal mandates? | The project is important to the accomplishment of State and Federal mandates | 8 | 3 | Mission Critical
19 | Does the project address State and Federal mandates? | The project is critical to accomplishment of State and Federal mandates | 12 | 5 | Mission Critical
20 | How politically sensitive is the project? |  |  | 0 | Failure
20 | How politically sensitive is the project? | Political climate has no impact on the project. |  | 0 | Failure
20 | How politically sensitive is the project? | Political climate has very little impact on the project. |  | 1 | Failure
20 | How politically sensitive is the project? | The project is sensitive to political climate. |  | 3 | Failure
20 | How politically sensitive is the project? | The project is very sensitive to political climate. |  | 5 | Failure
21 | How will the failure of the project impact the customers? |  | 0 | 0 | Failure
21 | How will the failure of the project impact the customers? | There is no impact of project failure on the customers | 0 | 0 | Failure
21 | How will the failure of the project impact the customers? | Impact of project failure on customers is minimal | 4 | 1 | Failure
21 | How will the failure of the project impact the customers? | Impact of project failure on customers is moderate | 8 | 3 | Failure
21 | How will the failure of the project impact the customers? | Impact of project failure on customers is high | 16 | 5 | Failure
22 | What is the anticipated involvement of the End Users with System Design and Testing? |  | 0 | 0
22 | What is the anticipated involvement of the End Users with System Design and Testing? | Not applicable | 0 | 0
22 | What is the anticipated involvement of the End Users with System Design and Testing? | Highly involved with development team, provide significant input and have significant ownership of system | 4 | 0
22 | What is the anticipated involvement of the End Users with System Design and Testing? | Play minor roles with development team or have moderate impact on system development | 6 | 0
22 | What is the anticipated involvement of the End Users with System Design and Testing? | Minimal or no user involvement with development team or little user input into process | 8 | 0
23 | What is the anticipated involvement of the End Users in the Definition of Project Requirements and Scope? |  | 0 | 0
23 | What is the anticipated involvement of the End Users in the Definition of Project Requirements and Scope? | Requirements well-established, baseline defined, user acceptance high with no changes | 2 | 0
23 | What is the anticipated involvement of the End Users in the Definition of Project Requirements and Scope? | Requirements well-established, baseline defined, user acceptance high, and few changes | 4 | 0
23 | What is the anticipated involvement of the End Users in the Definition of Project Requirements and Scope? | Requirements defined but changes to baseline expected; requirements may not have been distributed to all employees | 8 | 0
23 | What is the anticipated involvement of the End Users in the Definition of Project Requirements and Scope? | Rapidly changing size or scope; requirements not defined and not signed off by users | 16 | 0
24 | How important is the project to successful execution of Mason's core business activities? |  | 0 | 0 | Mission Critical
24 | How important is the project to successful execution of Mason's core business activities? | The project is/has little or no direct impact on current core business activities | 2 | 0 | Mission Critical
24 | How important is the project to successful execution of Mason's core business activities? | The project enhances organization core business activities | 4 | 1 | Mission Critical
24 | How important is the project to successful execution of Mason's core business activities? | The project is important to the organization core business activities | 6 | 3 | Mission Critical
24 | How important is the project to successful execution of Mason's core business activities? | The project is critical to the organization core business activities | 8 | 5 | Mission Critical
25 | How significant will the project’s impact be on the business process? |  | 0 | 0 | Complexity
25 | How significant will the project’s impact be on the business process? | No business process is impacted | 0 | 0 | Complexity
25 | How significant will the project’s impact be on the business process? | No critical processes are impacted | 4 | 1 | Complexity
25 | How significant will the project’s impact be on the business process? | Critical business processes are impacted | 6 | 3 | Complexity
25 | How significant will the project’s impact be on the business process? | A large portion of the business processes are impacted | 8 | 5 | Complexity
26 | How large of an organizational impact will the project have in the Commonwealth (beyond the impact to just George Mason University)? |  | 0 | 0 | Mission Critical
26 | How large of an organizational impact will the project have in the Commonwealth (beyond the impact to just George Mason University)? | Impacts a single division/unit/department | 2 | 0 | Mission Critical
26 | How large of an organizational impact will the project have in the Commonwealth (beyond the impact to just George Mason University)? | Impacts a number of divisions/units/department | 4 | 1 | Mission Critical
26 | How large of an organizational impact will the project have in the Commonwealth (beyond the impact to just George Mason University)? | Impacts all of Mason | 6 | 3 | Mission Critical
26 | How large of an organizational impact will the project have in the Commonwealth (beyond the impact to just George Mason University)? | Impacts Mason and other state agencies as well | 12 | 5 | Mission Critical
27 | Is the project using proven technology? |  | 0 | 0 | Complexity
27 | Is the project using proven technology? | The technology is proven and has been available for a number of years | 2 | 0 | Complexity
27 | Is the project using proven technology? | The technology has been available for several years | 4 | 1 | Complexity
27 | Is the project using proven technology? | The technology has been developed but is very new | 8 | 3 | Complexity
27 | Is the project using proven technology? | The technology is in development (Leading Edge) | 12 | 5 | Complexity
28 | Is the proposed solution applied in a New, Proven, or Tried way? |  | 0 | 0 | Complexity
28 | Is the proposed solution applied in a New, Proven, or Tried way? | Application of the technology is tried and proven | 3 | 0 | Complexity
28 | Is the proposed solution applied in a New, Proven, or Tried way? | An application of the technology has been tried and is partially proven | 6 | 1 | Complexity
28 | Is the proposed solution applied in a New, Proven, or Tried way? | A new application of the technology has been tried but is not proven | 9 | 3 | Complexity
28 | Is the proposed solution applied in a New, Proven, or Tried way? | A new application of the technology has never been tried before | 12 | 5 | Complexity
29 | What level of Data Conversion is required for the project (impact and complexity)? |  | 0 | 0 | External
29 | What level of Data Conversion is required for the project (impact and complexity)? | No data conversion is required | 0 | 0 | External
29 | What level of Data Conversion is required for the project (impact and complexity)? | Data conversion from other sources has little impact and/or is not complex | 4 | 1 | External
29 | What level of Data Conversion is required for the project (impact and complexity)? | Data conversion from other sources has some impact and/or is moderately complex | 6 | 3 | External
29 | What level of Data Conversion is required for the project (impact and complexity)? | Data conversion from other sources has a significant impact and/or is very complex | 8 | 5 | External
30 | What is the calculated Overall Risk level for the project? (Auto-filled from data above) |  | 0 | 0
30 | What is the calculated Overall Risk level for the project? (Auto-filled from data above) | No risk | 5 | 0
30 | What is the calculated Overall Risk level for the project? (Auto-filled from data above) | Low | 10 | 0
30 | What is the calculated Overall Risk level for the project? (Auto-filled from data above) | Medium | 20 | 0
30 | What is the calculated Overall Risk level for the project? (Auto-filled from data above) | High | 30 | 0
High | Initiation - Cost Benefit Analysis (template) Planning - Work Breakdown Structure (EPMO Tool) Planning - Project Schedule (EPMO Tool) Planning - Resource Plan (template) Planning - Budget Plan (template) Planning - Project Performance Plan (template) Planning - Procurement Plan (template) Planning - Risk Management Plan (template) Planning - Communications Plan (template) Planning - Change and Configuration Management Plan (template) Planning - Quality Management and IV&V Plan (template) Planning - Project Plan Executive Summary (template) Execution - Status Report (on-line form) Execution - Meeting Agendas and Minutes (per project) Execution - Procurement Documents and Log (on-line form / per project) Execution - Change Control Request (template) Execution - Issue Log and Issue Management (on-line form) Execution - User Acceptance (template) Closeout - Project Closeout Report (template)
Medium | Initiation - Cost Benefit Analysis (template) Planning - Work Breakdown Structure (EPMO Tool) Planning - Project Schedule (EPMO Tool) Planning - Budget Plan (template) Planning - Project Performance Plan (template) Planning - Procurement Plan (template) Planning - Risk Management Plan (template) Planning - Communications Plan (template) Planning - Change and Configuration Management Plan (template) Planning - Quality Management and IV&V Plan (template) Planning - Project Plan Executive Summary (template) Execution - Status Report (on-line form) Execution - Meeting Agendas and Minutes (per project) Execution - Procurement Documents and Log (on-line form / per project) Execution - Issue Log and Issue Management (on-line form) Execution - User Acceptance (template) Closeout - Project Closeout Report (template)
Low | Selection - Cost Benefit Analysis (template) Planning - Project Schedule (EPMO Tool) Planning - Budget Plan (template) Planning - Project Performance Plan (template) Planning - Risk Management Plan (template) Planning - Communications Plan (template) Planning - Quality Management and IV&V Plan (template) Planning - Project Plan Executive Summary (template) Execution - Status Report (on-line form) Execution - Meeting Agendas and Minutes (per project) Execution - Procurement Documents and Log (on-line form / per project) Execution - Issue Log and Issue Management (on-line form) Closeout - Project Closeout Report (template)
Basic | Selection - Cost Benefit Analysis (template) Planning - Project Schedule (EPMO Tool) Planning - Risk Management Plan (template) Planning - Communications Plan (template) Planning - Project Plan Executive Summary (template) Execution - Status Report (on-line form) Execution - Meeting Agendas and Minutes (per project) Execution - Procurement Documents and Log (on-line form / per project) Execution - Issue Log and Issue Management (on-line form)